DASH Platform

Minimum Work Requirements for Maintenance and Support to the End of 2026

Melbourne Dental School, University of Melbourne

# Background

In 2022 the Melbourne Dental School (MDS) agreed to adopt programmatic assessment across the Bachelor of Oral Health (BOH) and the Doctor of Dental Surgery (DDS). This approach suits health professions education, and since the School began implementing it, the University has recommended it as Principle 2 of its guidance on Assuring Learning in the Age of GenAI. The change is a large assessment modernisation project that brings the MDS closer to comparable dentistry and health professions programs.

Programmatic assessment rests on twelve principles that keep student assessment fair. More importantly, they allow progress decisions, whether a student passes or fails, to be made from multiple data points across varied assessments.

# About DASH

Programme-wide assessment depends on a platform and a data scientist to collect, collate and report the data, so that academics can make credible decisions and students can understand their own progress. DASH was created after the School trialled several platforms and weighed the cost against the benefit of an off-the-shelf third-party product. Its development has been governed by a University Privacy Impact Assessment.

Most third-party programs carry a high price for small disciplines, and they arrive with complex functionality that is far from plug and play. DASH instead provides a system built for purpose, giving subject coordinators immediate and longitudinal data to support progress decisions. A body of continuing work remains to take the platform to completion. Any school running this style of assessment needs dedicated data analysis support, since academic staff do not have the capacity to bring all the data together within the timeframe the dental school now achieves.

# Purpose of this document

The activities set out below are the minimum work required from Suhrid Gupta (full stack developer) and Kunal Patel (data scientist) to keep DASH stable, and to support academic staff, through to the end of the 2026 examination period.

Taken together, this work delivers a minimum viable product: a version of DASH that the University's remaining staff can maintain and use year to year, without further software development. Everything listed here is scoped to reach that point and no further.

# The 2026 assessment period

Six weeks of teaching remain, and they include several major assessments. SWOTVAC follows, allowing final assessment preparation, and then two weeks of intensive assessment. That period covers four OSCEs, three SCBD/Vivas and the BOH3 ECCA presentation, alongside the written assessments.

Final results are due on 4 December, so Boards of Examiners are likely to sit in the week of 23 November. The supplementary examination period runs from 11 to 18 December. Additional DDS2 OSCEs are already confirmed, with more detail on DDS4 expected shortly. Special consideration and supplementary assessments are likely across all performance and clinical hurdle assessments, where permitted, during the University supplementary period.

# Suhrid Gupta, Full Stack Developer

The activities below are ordered by priority, from the work that most directly protects the platform and the 2026 assessments through to ongoing coordination. Estimated hours reflect the effort needed to reach and maintain the minimum viable product described above.

| No. | Activity | Estimated effort |
| --- | --- | --- |
| 1 | CAF builder | 60–100 hours |
| 2 | AWS deployment cleanup and security | 28 hours (4 × 7-hour runs) |
| 3 | DASH email notification builder and support | 32 hours |
| 4 | DASH form configuration and data validation audit | 32 hours |
| 5 | All OSCEs (coordinator self-service and on-ground support) | Included in the hours above |
| 6 | DASH administrator actions for students and assessors | 10 hours |
| 7 | On-site support for major assessments | 4 full days (7.25 hrs) + 7 half days |
| 8 | Maintenance and audit jobs | 8 hours |
| 9 | Admin documentation and handover runbook | 8 hours |
| 10 | Assessment sub-committee and working group meetings | 8–10 hours |

## 1. CAF builder

Gives coordinators the ability to maintain and modify the CAF form structure without a developer. This is needed so that assessment data is not lost and the program is ready for use in January, in time for the 2027 cohort. It is the single largest step towards running DASH year to year without further software development.

Estimated effort: 60–100 hours

Staff involved: Clare McNally

## 2. AWS deployment cleanup and security

Required by the University's Application Security Specialists to keep the application and its deployment free of security vulnerabilities. The work is ongoing and monitored by the University together with Suhrid. A run takes about 7 hours and happens roughly once a month; an additional run is under way in response to a University request. The deployment code also needs some optimisation, as there is redundancy in the way it is currently deployed.

Estimated effort: 7 hours for the additional September run, plus standard 7-hour runs in September, October and November (28 hours total).

Staff involved: Ronald Michael (Application Security Specialist)

## 3. DASH email notification builder and support

One of the most important items as the year closes and through the final six weeks of ongoing simulation and clinical assessments. Automatic notifications let subject coordinators and component convenors reach out to students and provide immediate support. This can prevent students from failing, help identify students at risk of failing, and allow coordinators to build a body of evidence should an appeal arise.

Estimated effort: 32 hours

Staff involved: Clare McNally, Amy Thompson, Mat Lim, Bree Jones, Monica Ramzy, Elice Chen, Ben Ross, Eunice Powell, Katharine Dal Santo, Madeline Townsend, Michael Wylie, Aditi Bhide, Amber Stevanov, Sophie McKenna, Yvonne Zhang, Keira Venables

## 4. DASH form configuration and data validation audit

Makes sure the data stored in the backend is never malformed or corrupted. The audit confirms that the backend rejects any malformed or corrupt data, and that it never rewrites correct data.

Coverage spans every assessment form across the programme: DDS1 simulation assessment forms (Perio and Cons Dent); DDS2 simulation and clinical assessment forms, and SCBDs; DDS3 clinical assessment forms, SCBDs and OSCEs; DDS4 clinical assessment forms and case presentation; BOH1 simulation assessment forms and OSCE; BOH2 clinical assessment forms, viva voce and OSCE; BOH3 clinical assessment forms, viva voce and oral presentation.

Estimated effort: 32 hours

Staff involved: Clare McNally, Amy Thompson, Mat Lim, Bree Jones, Monica Ramzy, Elice Chen, Ben Ross, Eunice Powell, Katharine Dal Santo, Madeline Townsend, Michael Wylie, Aditi Bhide, Amber Stevanov, Sophie McKenna, Yvonne Zhang, Keira Venables, Roisin McGrath

## 5. All OSCEs

Of all the assessments, the OSCE is the largest, generating between 900 and 1400 forms per cohort. The platform is being extended so that coordinators can develop their own OSCE, trialled with DDS2 and DDS4 in September (week of 7 to 11 September). It needs on-ground support for academics at the time of the OSCE, together with preparation support.

Estimated effort: Included in the hours above.

Staff involved: Clare McNally, Amy Thompson, Mat Lim, Elice Chen, Ben Ross, Katharine Dal Santo, Madeline Townsend, Michael Wylie, Aditi Bhide, Amber Stevanov, Sophie McKenna, Yvonne Zhang, Keira Venables

## 6. DASH administrator actions for students and assessors

Day-to-day administrative actions carried out on request: modifying CAF form data where it is incorrect, reopening student or assessor forms for the user, and viewing CAF form logs.

Estimated effort: 10 hours

Staff involved: All coordinators, on demand; all students, on demand

## 7. On-site support for major assessments

On-site or on-call presence so that each major assessment runs smoothly and everyone is logged in. OSCEs usually need the full day; SCBDs, case presentations and vivas need a half day. The half days can be managed on call from the main computer at home, but OSCEs need to be attended on site.

Sessions covered: DDS1 OSCE (full day); DDS2 SCBDs (half day); DDS3 SCBDs (half day); DDS3 OSCEs (full day); DDS4 case presentation (half day); BOH1 OSCE (full day); BOH2 viva voce (half day); BOH2 OSCE (full day); BOH3 viva voce (half day); BOH3 oral presentation across ORAL30001 and ORAL30002 (half day, twice).

Estimated effort: 4 full days at 7.25 hours, plus 7 half days.

Staff involved: Clare McNally, Amy Thompson, Mat Lim, Elice Chen, Ben Ross, Eunice Powell, Katharine Dal Santo, Madeline Townsend, Michael Wylie, Aditi Bhide, Amber Stevanov, Sophie McKenna, Yvonne Zhang, Keira Venables, Roisin McGrath

## 8. Maintenance and audit jobs

Backend optimisation such as log pruning and deleting data after a set number of years. This keeps the database from reaching memory limits and supports security compliance.

Estimated effort: 8 hours

Staff involved: All coordinators, on demand; all students, on demand

## 9. Admin documentation and handover runbook

Handover documentation describing how DASH functions and covering all of its features, written for whoever maintains the platform after the current team steps back.

Estimated effort: 8 hours

Staff involved: Clare McNally

## 10. Assessment sub-committee and working group meetings

Regular meetings, monthly or fortnightly, with each group: the simulation and clinical assessment working group, and the OSCE and major clinical assessment working group. Ad hoc meetings arise as well, particularly with the sim and clinical assessment teams. The OSCE and major clinical assessment meetings increase in the lead-up to the end-of-year assessments.

Estimated effort: 8–10 hours

Staff involved: Clare McNally, Jodie Tamblyn, Amy Thompson, Monica Ramzy, Michael Wylie, Sarah Laing

# Kunal Patel, Data Scientist

The activities below cover the data science, reporting, and analysis workload required to support academic staff and Boards of Examiners through the end of 2026.

| Activity | Hours | Staff/people involved |
| --- | --- | --- |
| Master of Data Science project support 2x groups of 5-7 students 1x hourly meeting with each group (meeting frequency increasing as they get to the end of their project and their final assessment is due) 30 minutes of work each week to support each group | 3 hours/week 1-2 hours of support for final major assessment (oral presentation and major report including dashboard and full code to support assessment decisions) | Clare McNally 2 groups of Master of Data Science Students – 1x hourly meeting per group |
| DDS2 Student research projects 5 groups across 3 projects (20 students) Ethics applications Development of data set Data interpretation and analysis support 1x hour meeting each fortnight per group 30 minutes per group preparation support each fortnight (depending on progress and assessment timing) | 15 hours of meetings till end of teaching period 7.5 hours of pre/post meeting support 1-2 hours of support for final major assessment (oral presentations and literature review) | Clare McNally Michael Wylie Sarah Laing Jodie Tamblyn Monica Ramzy Suhrid Gupta 20 students in DDS2 who will move to continue the projects in DDS3 - 2027 |
| Ongoing simulation and clinical assessment reporting for students DDS1 – Perio and Cons Dent sim reports DDS2 – Endo, Fixed Pros and Paeds Sim, GP, Rem Pros, Perio clinics DDS3 – All general and specialist clinic forms, Ortho sim and other observation forms DDS4 – End of year clinical assessment completion – with specific recommendations for progress to graduation BOH1 – Simulation and Intro to clinic forms BOH2 – Paeds and GP sim, GP, Perio and Smile Squad clinics BOH3 – End of year clinical assessment completion – with specific recommendations for progress to graduation Each student receives a mail out every fortnight of their progress, these reports are shared with subject coordinators and convenors where relevant. | ~12 hr/fortnight | Amy Thompson Mat Lim Bree Jones Monica Ramzy Elice Chen Ben Ross Eunice Powell Katharine Dal Santo Madeline Townsend Michael Wylie Aditi Bhide (& Shailly Luthra) Amber Stevanov Sophie McKenna Yvonne Zhang Keira Venables |
| Flagging and comprehensive performance reports for coordinators of all cohorts On demand Regular every week In preparation for Board of Examiner and Progress Review Panel meetings | 3hr/week + 5 hr for BOE and Progress Review Reports | Amy Thompson Mat Lim Bree Jones Monica Ramzy Elice Chen Ben Ross Eunice Powell Katharine Dal Santo Madeline Townsend Michael Wylie Aditi Bhide (& Shailly Luthra) Amber Stevanov Sophie McKenna Yvonne Zhang Keira Venables |
| Flagging and comprehensive performance report modifications There are constant changes to reports based on feedback from coordinators Feedback reports are also prepared for student meetings (particularly BOH3) | 6hr/week |  |
| CAF form checklists/items modification support | 1hr/week | Clare McNally |
| OSCE support and reporting DDS1 OSCE (November) DDS2 OSCE (September) DDS3 OSCE (November) DDS4 OSCE (September) BOH1 OSCE (November) BOH2 OSCE (November) Support with pre-OSCE assessment development. Preparation of code to automate reporting of all OSCE data On-site support for the assessment Immediate data presentation to subject coordinators within 1-2 hours of completion of each OSCE Preparation of final data reports for use at the Board of Examiners within 5 days of completion of each OSCE | 96 hours | Clare McNally Amy Thompson Mat Lim Elice Chen Ben Ross Katharine Dal Santo Madeline Townsend Michael Wylie Aditi Bhide Amber Stevanov Sophie McKenna Yvonne Zhang Keira Venables |
| Other assessment analysis and support Viva BOH3 (September) DDS4 (November) BOH2 (November) Oral/Case Pres BOH3 (September and October) DDS4 (November) SCBD DDS2 (November) DDS3 (2x October) The time involves meeting with the coordinators to refine the data and assessment for final analysis for all the assessments | ~32 hours | Clare McNally Amy Thompson Mat Lim Elice Chen Ben Ross Eunice Powell Katharine Dal Santo Madeline Townsend Michael Wylie Aditi Bhide Amber Stevanov Sophie McKenna Yvonne Zhang Keira Venables |
| Professional behaviour notification reporting A summation report of the PBNs linked to all other performance data Provided to subject coordinators with end of year ongoing sim, clinic and major assessment reports | 2 hours | Clare McNally All subject coordinators Board of Examiners |
| Student leave analysis A summation report of the PBNs linked to all other performance data Provided to subject coordinators with end of year ongoing sim, clinic and major assessment reports | 2 hours | Clare McNally All subject coordinators Board of Examiners |
| Written exams reporting An aspect of the Assessment Sub-committee through the Written Assessment Working Group that has only been adopted in 2025/2026. Subject coordinators, convenors and senior T&L leadership seek reports on the performance of written assessment items Particularly used when there are many high performing students | ~20 hours | Clare McNally All subject coordinators with written exams Board of Examiners |
| Overall progress reports In line with the principles of programmatic assessment, we have started to triangulate data to understand student progress across subjects and domains. Still in development, end of year 2026 will be the first opportunity to conduct this type of analysis and present subject coordinators with whole of subject assessment reporting (for all clinical assessments) On request attendance at BOE meetings to understand any alternate or new requests for data reporting | ~10 hours | All BOH and DDS Board of Examiners |
| DCD Ongoing Simulation and Clinical Assessment reporting Ortho Pros Paeds Oral Med Possibly EOY Special Needs Unsure if other disciplines have engaged in the ongoing CAF this year Monthly reports and EOY summary reports | ~ 4 hours/month | Marie Cornelius Jaafar Abduo Mihiri Silva Michael McCullough ~Mat Lim |